## Sheet1
Timeline Of Events On Transmission Connectivity_600 MW PSP at Indravati (Mukhiguda)
YEAR |  | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
MONTH | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | DEC
Route survey for Transmission Network
Preparation of Land schedule and Land required from Mukhiguda PSP site to 400/220KV proposed GSS at Theruvali.
Forest Clearance for Transmission Connectivity
soil investigation
Preparation of DPR and Project Estimate
Approval of Budget from Govt
Transmission Network
PREPARATION OF TENDER DOCUMENTS, TENDERING & AWARD OF CONTRACT
CHECK SURVEY AND MOBILISATION
SUPPLY OF MATERIALS
CIVIL & ERECTION WORK
TESTING & COMMISSIONING
7400 Lakhs
11100 Lakhs
18241 Lakhs

## Sheet2 (hidden)
529201237
5292.0124
529.2012 | 0.20124 | 529
3175.2074 | 0.20742 | 3175
1587.6037 | 1588.0124 | 1588.0124