## Sheet1
BAR CHART FOR SUB-STATION ISOLATOR & MECHANISM BOX UPGRADATION.- ₹ 3041 LAKHS
YEAR | 2026 | [8 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029
MONTH | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
FUNDING ARRANGEMENTS
PREPARATION OF TENDER DOCUMENTS, TENDERING & AWARD OF CONTRACT
SUPPLY OF MATERIALS
ERECTION & RETROFITTING
TESTING & COMMISSIONING
FUNDS REQUIREMENT [RS.IN LAKHS] | 2026 APR: 375; 2027 JAN: 1877; 2028 JAN: 751; 2029 JAN: 38