## Sheet1
CAPEX TRANSMISSION PROJECTS FY 2021-22
Sl. No. | Description of the Project/Scheme |  |  | Expenditure during FY 2020-21 |  |  | Projected expenditure FY 2021-22
A | ONGOING SCHEME | Commision Approval Order No. and Date | Source of Funding | Actual For First Six Months | Projection For Balance Six Months | Total |  | Scheduled date of completion
1 | 2 | 3 | 4 | 3 | 4 | 5 | 6 | 11
1 | 132kV Bhadrak-Anandpur S/C line | 1. 05/2016 (BP) 30.07.2016 | RRCP |  | 2.8 | 2.8 | 2 | Completed
2 | 132/33kV Agarpada S/S with line | 1. 60/2016 (IP) 18.10.2017 | OWN | 0.06 | 10.01 | 10.07 |  | Completed
3 | 220/132kV Atri (Karadagadia) S/S with line | 1. 05/2016 (BP) 30.07.2016 |  | 2.4 | 1.6 | 4 |  | Completed
4 | 220/132/33kV Pratapsasan S/S with line | 1. 05/2016 (BP) 30.07.2016 2. 8/2013 (IP) 04.06.2014 | SCRIPS | 4 | 4 | 8 | 6.65 | 3/2021
5 | 3rd ICT at 400/220kV New Duburi S/S | 14th TP (Yet to Approve) | OWN | 1.02 | 4.8 | 5.82 |  | 3/2021
6 | 2X20MVA, 132/33kV R.Udayagiri S/S with line | 1. 05/2016 (BP) 30.07.2016 2. 3/2013 (IP) 21.03.2014 | Govt. Funding | 2.13 | 0.64 | 2.77 |  | 1/2021
7 | 132/33kV Brajabiharipur, Cuttack with LILO. | 1. 05/2016 (BP) 30.07.2016 2. 113/2012 (IP) 10.02.2014 | SCRIPS | 3.28 | 7.15 | 10.43 |  | Completed
8 | 220/33kV Baliguda S/S with 220kV Kesinga Baliguda DC line | 1. 05/2016 (BP) 30.07.2016 2. 113/2012 (IP) 10.02.2014 | OWN | 1.6 | 3.4 | 5 | 0.68 | 12/2021
9 | 132/33kV Satasankha (Puri) S/S with line | 1. 05/2016 (BP) 30.07.2016 2. 3/2013 (IP) 21.03.2014 | Govt. Funding | 2.5 | 0.5 | 3 |  | Completed
10 | 132/33kV Betanati S/S with line | 1. 05/2016 (BP) 30.07.2016 2. 2/2013 (IP) 12.03.2014 | OWN |  | 8.46 | 8.46 | 3 | Completed
11 | 220/132/33kV Aska S/S with line | 1. 05/2016 (BP) 30.07.2016 2. 2/2013 (IP) 12.03.2014 | OWN | 1.42 | 0.1 | 1.52 |  | Completed
12 | 220/132/33kV Goda Chhak S/S with line | 1. 05/2016 (BP) 30.07.2016 2. 2/2013 (IP) 12.03.2014 | OWN |  | 2.15 | 2.15 | 2 | Completed
13 | 132/33kV Unit-8 (BBSR) GIS S/S with line | 1. 05/2016 (BP) 30.07.2016 | SCRIPS | - | 6.04 | 6.04 |  | Completed
14 | 132/33kV Mancheswar GIS S/S with line | 1. 05/2016 (BP) 30.07.2016 | SCRIPS | 1.2 | 7.39 | 8.59 |  | Completed
15 | 132kV Phulbani-Boudh S/C line | 1. 05/2016 (BP) 30.07.2016 | RRCP | 1.42 | 2.32 | 3.74 | 3 | 7/2021
16 | 132kV DC line from 132/33kV GIS Chandbali to 220/132/33kV Grid sub-station, Balimunda, Dhamara. |  | DRPS | 0.89 | 2.7 | 3.59 | 6.06 | 6/2021
17 | 220kV Pandiabil-Pratapsasan D/C line | 1. 05/2016 (BP) 30.07.2016 | DRPS | 0.31 | 8.58 | 8.89 | 2 | 3/2021
18 | 220/132/33kV Balimunda, Dhamra S/S with line (Revival) | 1. 05/2016 (BP) 30.07.2016 2. 78/2010 (IP) 05.08.2010 | OWN | 14.82 | 25.18 | 40 | 25.25 | 5/2021
19 | 132/33kV G.Udaygiri S/S with line | 1. 60/2016 (IP) 18.10.2017 | OWN | 7.24 | 21.46 | 28.7 |  | 1/2021
20 | 400/220kV GIS at Meramundali-B | 1. 05/2016 (BP) 30.07.2016 | OWN | 15.68 | 22.85 | 38.53 | 15.87 | 3/2021
21 | 220/33kV S/S at Dasapalla with line | 1. 05/2016 (BP) 30.07.2016 | JICA | 4.18 | 8 | 12.18 | 23.19 | 1/2022
22 | 220/132/33kV S/S at Kiakata with line | 1. 60/2016 (IP) 18.10.2017 | JICA | 8.64 | 21.36 | 30 | 39 | 1/2022
23 | 132/33kV S/S at Rajnagar with line | 1. 05/2016 (BP) 30.07.2016 | JICA | 3.39 | 12.76 | 16.15 | 10.5 | 4/2021
24 | 132kV Kuchei-Bangiriposi S/C line | 14th TP (Yet to Approve) | OWN | 1.15 | 4.69 | 5.84 | 2 | 6/2021
25 | 220/33kV S/S at Telkoi with line | 1. 05/2016 (BP) 30.07.2016 | OWN | 6.15 | 14.61 | 20.76 | 12.42 | 5/2021
26 | 132kV Aska-Digapahandi D/C line | 1. 05/2016 (BP) 30.07.2016 | DRPS | 2.68 | 1.32 | 4 |  | 1/2021
27 | 220kV Theruvali-Narendrapur to Aska line | 14th TP (Yet to Approve) | OWN | 6.06 | 10.56 | 16.62 | 10.15 | 6/2021
28 | 132kV Parlakhemundi -R.Udaygiri D/C line | 14th TP (Yet to Approve) | RRCP | 2.34 | 7.66 | 10 | 14.01 | 3/2021
29 | 132/33kV S/S at Gondia with line | 1. 60/2016 (IP) 18.10.2017 | JICA | 3.97 | 13.13 | 17.1 | 6.11 | 4/2021
30 | 220/132/33kV S/S at Turumunga with line | 1. 18/2017 (TP) 09.04.2019 2. 05/2016 (BP) 30.07.2016 | JICA | 7.33 | 21.67 | 29 | 4 | 10/2021
31 | 132/33kV S/S at Chandipur with line | 1. 05/2016 (BP) 30.07.2016 | JICA | 1.82 | 11.04 | 12.86 | 9.65 | 8/2022
32 | 132/33kV S/S at Bahugram with line | 1. 60/2016 (IP) 18.10.2017 | JICA | 8.05 | 5.41 | 13.46 | 10.5 | 6/2021
33 | 220/33kV S/S at Palei, Balichandrapur with line | 14th TP (Yet to Approve) | Own | 1.36 | 4.64 | 6 | 32.36 | 12/2021
34 | Diversion of one no. 400kV and 4nos 220kV line with 220kV LILO arrangement for connectivity with 400/220kV GIS Meramundali-B. | 1. 05/2016 (BP) 30.07.2016 | OWN | 1.27 | 10.31 | 11.58 | 22 | 3/2021
35 | 132/33kV GIS at Hinjuli | 14th TP (Yet to Approve) | OWN | 5.67 | 15.14 | 20.81 | 5 | 6/2021
36 | 220/33kV GIS at Godisahi | 1. 18/2017 (TP) 09.04.2019 | SCRIPS | 0.65 | 18.59 | 19.24 | 14.43 | 8/2022
37 | 220/33kV GIS at Gothapatna (Kantabada) | 1. 18/2017 (TP) 09.04.2019 | SCRIPS | 6.62 | 12.62 | 19.24 | 14.43 | 8/2022
38 | 132/33kV GIS at Nayapalli | 14th TP (Yet to Approve) | SCRIPS | 0.14 | 19.86 | 20 | 47.88 | 3/2022
39 | 132/33kV GIS at Satyanagar | 1. 18/2017 (TP) 09.04.2019 | SCRIPS | 2.21 | 10.79 | 13 | 40.75 | 6/2022
40 | 132/33kV GIS at Badagada | 1. 18/2017 (TP) 09.04.2019 | SCRIPS | 0.55 | 10.45 | 11 | 40.75 | 6/2022
41 | 220/132/33kV GIS at Balianata | 1. 18/2017 (TP) 09.04.2019 | SCRIPS | 0.65 | 55.23 | 55.88 | 41.92 | 12/2021
42 | Other works |  |  | 1.85 |  | 1.85
43 | Restoration of 400kV IB-Meramundali DC line from Loc No. 124/2 (Bhusan) to 149/0 (OPGC). Est No. 11/2015-16. |  |  |  | 0.5 | 0.5 | - | Completed
44 | 220/132/33kV S/s at Lapanga. |  |  |  | 0.29 | 0.29 |  | Completed
45 | 220/132/33kV S/s at Kuanrmunda | 1. 05/2016 (BP) 30.07.2016 2. 22/2010 (IP) 03.09.2010 | 23.30 cr. Equity Govt. Funding | 4.52 | 12.84 | 17.36 | 15 | 5/2021
46 | 400/220kV S/s at Lapanga. | 1. 05/2016 (BP) 30.07.2016 2. 3/2013 (IP) 21.03.2014 | OWN | 0.68 | 0.19 | 0.87 |  | Completed
47 | 132/33kV S/s at Maneswar | 1. 05/2016 (BP) 30.07.2016 2. 8/2013 (IP) 04.06.2014 | OWN |  | 12.67 | 12.67 |  | 1/2021
48 | 132/33kV S/s at Hirakud | 1. 05/2016 (BP) 30.07.2016 | OWN | 4.41 | 6.74 | 11.15 | 14.42 | 2/2021
49 | 220/132/33 kV Grid Sub-Station at Bamra. (50% Deposit Work) | 1. 18/2017 (TP) 09.04.2019 | OWN | 10.54 | 9.59 | 20.13 | 15.16 | 12/2021
50 | 132/33kV Pottangi S/S with line | 1. 05/2016 (BP) 30.07.2016 2. 113/2012 (IP) 10.02.2014 | OWN | 0.13 | 1.6 | 1.73 |  | Completed
51 | 132kV Umerkote S/S with line |  |  |  | 1.3 | 1.3 |  | Completed
52 | 132/33kV Podagada S/S with line |  |  | 0.02 | 1.4 | 1.42 |  | Completed
53 | 220kV Jayanagar- PGCIL D/C line with 2 nos. 220kV feeder bays | 1. 05/2016 (BP) 30.07.2016 2. 43/2012 (IP) 23.06.2012 | REC | 0.09 | 0.5 | 0.59 |  | Completed
54 | Conversion of existing Jaynagar- Sunabeda S/C line to D/C line | 1. 05/2016 (BP) 30.07.2016 | 9.72 cr. Equity | 0.21 | 7.38 | 7.59 |  | 1/2021
55 | 220/33kV Malkanagiri S/S with line |  |  |  | 3 | 3
56 | 132/33kV Boriguma S/S with LILO | 1. 05/2016 (BP) 30.07.2016 2. 2/2013 (IP) 12.03.2014 | OWN |  | 8.59 | 8.59 | 10.2 | 3/2021
57 | 220/33kV Kalimela S/S with line | 1. 60/2016 (IP) 18.10.2017 | OWN | 2.82 | 3 | 5.82 |  | 6/2021
58 | 132kV Jayanagar -Tentulikhunti S/C line | 1. 05/2016 (BP) 30.07.2016 | OWN | 1.59 | 1.5 | 3.09 |  | 1/2021
59 | 220/33kV Govindpalli S/S with line | 1. 18/2017 (TP) 09.04.2019 | JICA | 2.83 | 3 | 5.83 |  | S/s charged on 17.11.20
60 | 132kV Podagada-Pottangi S/C line | 1. 05/2016 (BP) 30.07.2016 | RRCP | 1.44 | 4.5 | 5.94 |  | 3/2021
61 | 220/33kV S/s at Kashipur | 1. 05/2016 (BP) 30.07.2016 2. 2/2013 (IP) 12.03.2014 | OWN | - | 1.27 | 1.27 | - | Completed
62 | 220/132/33kV S/s at Jayapatna | 1. 05/2016 (BP) 30.07.2016 2. 2/2013 (IP) 12.03.2014 | OWN | 1.49 | 4.51 | 6 | 5 | Completed
63 | Installation of 20 MVA 220/33kV at 220/33kV Grid S/S Laxmipur. |  | OWN | - | 1.4 | 1.4 |  | Completed
64 | 220/132/33kV Grid S/s at Gunupur | 1. 18/2017 (TP) 09.04.2019 | JICA | 7.49 | 22.51 | 30 | 20 | 3/2021
65 | 220/132kV Kesinga S/S with line | 1. 05/2016 (BP) 30.07.2016 2. 27/2011 (IP) 25.06.2011 | 28.88 cr.Equity Govt. Funding | 1.03 | 12 | 13.03 | 2 | 3/2021
66 | 220/132/33kV Baragarh(New) S/S |  |  | - | 0.3 | 0.3 | - | Completed
67 | 132/33kV Kantabanji S/S with line |  |  | 0.03 | - | 0.03 | - | Completed
68 | 132kV Biramaharajapur S/S with line | 1. 05/2016 (BP) 30.07.2016 | OWN | 2.34 | 12.29 | 14.63 | 6 | 3/2021
69 | 132kV Junagarh-Kesinga D/C line | 1. 05/2016 (BP) 30.07.2016 | OWN | 0.15 | 0.2 | 0.35 | - | Completed
70 | 132kV Nuapada-Padampur line | 1. 05/2016 (BP) 30.07.2016 | RRCP | 1.03 | 10 | 11.03 | 5 | 3/2021
71 | 132/33kV Nabarangpur S/S | 14th TP (Yet to Approve) | OWN | 3.78 | 17.39 | 21.17 | 1.5 | 5/2021
72 | 132/33kV Lamataput S/S | 14th TP (Yet to Approve) | OWN | 4.42 | 6.26 | 10.68 | 15 | 10/2021
73 | 132kV DC Line From Baner to Jayapatna |  | Govt Funded | 0.19 | 1.31 | 1.5 |  | Completed
74 | 132kV DC Line on DC tower from Jaipatna (Baner) to Junagarh |  | OWN | 1.4 | 8.6 | 10 | 18.62 | 8/2021
75 | 220kV LILO of Bolangir-Kesinga line to 400/220kV Madhiapali | 1. 05/2016 (BP) 30.07.2016 2. 27/2011 (IP) 25.06.2011 | Equity Govt. Funding | - | 0.5 | 0.5 | - | 3/2021
76 | 132kV LILO of Bargarh-Barpali line to 220/132/33kV Bargarh |  | own | - | 0.9 | 0.9 |  | 1/2021
77 | 132/33kV Bhatli S/S with line | 1. 05/2016 (BP) 30.07.2016 | OWN | 3.9 | 20 | 23.9 | 12.22 | 3/2021
78 | 220/33 kV S/s at Deogarh | 1. 05/2016 (BP) 30.07.2016 | JICA | 4.2 | 5.54 | 9.74 | 2.28 | 2/2021
79 | 220/33kV Grid S/s at Lephripada | 1. 05/2016 (BP) 30.07.2016 | JICA | 2.38 | 6.6 | 8.98 | 6.45 | 6/2021
80 | 132/33kV S/s at Lakhanpur | 1. 05/2016 (BP) 30.07.2016 | JICA | 2.72 | 8.25 | 10.97 | 3.51 | 6/2021
81 | 132/33kV Thuapalli S/S with line | 1. 05/2016 (BP) 30.07.2016 | JICA | 3.28 | 16 | 19.28 | 4 | 2/2021
82 | 132 KV D/C line from Lapanga to Brajarajnagar | 1. 05/2016 (BP) 30.07.2016 | RRCP | 0.21 | 2.57 | 2.78 | 3.85 | 10/2021
| TOTAL OF A |  |  | 206.01 | 668.96 | 874.97 | 627.77
B | NEW PROJECTS
1 | 400/220kV GIS at Ramakrushnapur | 1. 18/2017 (TP) 09.04.2019 | JICA |  |  |  | 36.8 | 2023-24
2 | 400/220kV S/S at Khuntuni | 14th TP (Yet to Approve) | Govt Funded |  |  |  | 80 | 2023-24
3 | 220/132kV GIS at Dhenkanal-B | 1. 18/2017 (TP) 09.04.2019 | JICA |  |  |  | 30 | 2023-24
4 | 220/132/33kV GIS at Kuakhia | 1. 05/2016 (BP) 30.07.2016 | JICA | - |  |  | 23 | 2023-24
5 | 220kV LILO of 220kV TTPS-Joda to 220/33kV GIS Kekonjhar | 14th TP (Yet to Approve) |  | 0.62 | 1.38 | 2 | 18
6 | 400/220/33kV GIS at Paradeep with line | 1. 18/2017 (TP) 09.04.2019 |  |  |  |  | 80 | 2023-24
7 | 400kV & 220kV LILO line to 400/220kV GIS at Ramakrishnapur, 220kV & 132kV LILO line to GIS at Kuakhia & 220kV LILO line to GIS at Dhenkanal-B | 1. 18/2017 (TP) 09.04.2019 | JICA |  |  |  | 36.88 | 2023-24
8 | 400/220kV GIS S/s at Narendrapur | 1. 18/2017 (TP) 09.04.2019 | Govt Funded |  |  |  | 80 | 2023-24
9 | 220/132kV S/S at Nuapada | 14th TP (Yet to Approve) |  |  |  |  | 35.59 | 2023-24
10 | 132kV line 2nd Circuit from Bhadrak to Anandpur | 14th TP (Yet to Approve) |  |  |  |  | 3 | 2023-24
11 | 400kV DC line from 400/220kV Narendrapur S/s to 400kV S/s of PGCIL at Jeypore with LILO at Theruvali with Bay Extn. | 14th TP (Yet to Approve) | Govt Funded |  |  |  | 60 | 2023-24
12 | 132/33kV S/s at Brundabahal | 14th TP (Yet to Approve) | Govt Funded |  |  |  | 30 | 2023-24
13 | 132/33kV S/S Tarbha | 14th TP (Yet to Approve) | Govt Funded |  |  |  | 20 | 2023-24
14 | 132kV UG cabling from Arugul- Ransinghpur |  | RRCP |  |  |  | 14.63 | 2022-23
15 | 220kV Balimela- Jayanagr LILO at Govindpalli |  | RRCP |  |  |  | 1.51 | 2022-23
16 | 132kV SC on DC tower Kantabanji- patnagarh |  | RRCP |  |  |  | 5.69 | 2022-23
17 | 132kV LILO Budipadar-Sundargarh at Bamra |  | RRCP |  |  |  | 5.69 | 2022-23
18 | 132kV SC on DC tower Ghens-Padamapur |  | RRCP |  |  |  | 4.55 | 2022-23
19 | 132kV LILO Chhend -Nuagaon at Kuarnrmunda |  | RRCP |  |  |  | 1.72 | 2022-23
| TOTAL OF B |  |  | 0.62 | 1.38 | 2 | 567.06
C | DEPOSIT WORK
1 | RTSS at Kendrapara |  |  | 0.69 | 0.31 | 1
2 | RTSS at SIJU |  |  | 0.85 | 0.63 | 1.48
3 | RTSS at Charbatia |  |  | 0.34 | 3.66 | 4
4 | RTSS at Sukinda |  |  | 0.38 | 1.62 | 2
5 | RTSS at Dhanmandal |  |  | 0.99 | 3.01 | 4
6 | Kharasrota (knpd-Marsh)-9 Loc |  |  | 1.26 | 2.74 | 4
7 | Kharasrota (NWW)-7 Loc |  |  | 0.86 | 3.14 | 4
8 | 220kV 2 phase line on DC tower from Bonai to RTSS Bimalagarh |  |  | 0.09 | 2.25 | 2.34 | 0.16
9 | 132kV DC line(4 conductor) from Brajarajnagar to RTSS at Belpahar |  |  | 0.32 | 3.96 | 4.28 | 0.29
10 | 132 kV DC line(2 conductor) from Brajarajnagar to RTSS at Kechhobahal |  |  | 0.86 | 1 | 1.86
11 | 132kV S/c (2 Conductor) line from Lapanga to RTSS Rengali |  |  | 1.1 | 1 | 2.1
12 | 132kV S/c (2 Conductor) line from Maneswar to RTSS Maneswar |  |  |  | 2.79 | 2.79
13 | Diversion of 132kV D/C Line from NSPCL, Rourkela to MSDS-V, SAIL, RSP |  |  | 0.08 | 0.68 | 0.76
14 | 220/132/33kV Grid S/s at Bamra. (50% Deposit Work) |  |  | 10.54 | 13.59 | 24.13 | 14.16
15 | 132kV D/c (4 conductor) line from Bamra to RTSS, Dhutra |  |  | 3.23 | 9.73 | 12.96 | 6.49
16 | 132kV D/C (4 Conductor) line from Bamra to RTSS, Garposh |  |  | 0.92 | 3.91 | 4.83 | 2.61
17 | 132kV D/C (4 Conductor) line from Bamra to RTSS, Bamra |  |  | 0.08 | 0.23 | 0.31 | 0.93
18 | 132kV SC Line (Two phase) from Muniguda to RTSS at Bisamcuttack |  |  | 0.32 | 0.18 | 0.5 | -
19 | 220kV SC (2phase) line from Therubali to RTSS Bhalumaska |  |  | 0.15 | 1.35 | 1.5 | 2
20 | 132kV SC ( 2 phase) Traction line from Bhawanipatna to RTSS Lanjigarh |  |  | 0.51 | 1.49 | 2 | -
21 | 220kV Traction line from Laxmipur to RTSS Laxmipur. |  |  | 1.3 | 4.43 | 5.73 | 2
22 | RTSS at Kesinga |  |  | 0.6 | - | 0.6 | -
23 | RTSS at Nuapada |  |  | 0.44 | 0.3 | 0.74 | -
24 | RTSS at Dunguripali |  |  | - | 0.5 | 0.5 | -
25 | RTSS at Deogaon |  |  | 0.6 | 0.8 | 1.4 | 0.5
26 | RTSS at Godbhaga |  |  | - | 2 | 2 | 1
27 | 132kV 2Phase line from Bhawanipatna to Bhawanipatna RTSS |  |  | - | 2.3 | 2.3 | 0.7
28 | 132kV 2 Phase line from Gunupur to Palasingh RTSS |  |  | - | 6 | 6 | 4
| TOTAL of C |  |  | 26.5 | 73.6 | 100.1 | 34.84
D | TOTAL -Construction) D = A+B+C |  |  | 233.14 | 743.93 | 977.07 | 1229.67