## Sheet1
Sl No | Name of work | Total project cost ( in crores ) | Expenditure till 31.12.2020 | Physical progress of works | Proposed expenditure for FY 2020-21( in crores) | Proposed expenditure for FY 21-22 (in crores) | Proposed expenditure for FY 2022-23 (in crores) | Proposed expenditure for FY 2023-24 (in crores)
1 | Const. Of Multistoried office building of OPTCL, Tulasipur, Cuttack.(G+3) Total built up area-1212 sqm | 5.28 | 3.76 | The building has been completed in all aspects, hand over to O&M is pending. | 1.52
2 | Const. Of multi-stored office of Sr. G.M at Bidyutpuri Colony, Berhampur (G+3) Total built up area- 2950 sqm | 8.74 | 0.98 | Core structure in progress | 2.12 | 2.95 | 2.69
3 | Const. of multi-storied building, Matiasahi Anugul (G+3) Total built up area- 1288 sqm | 4.1 | 0.97 | Core structure completed, finishing works in progress. | 2 | 1.13
4 | Const. of multi-storied building, Jeypore (G+3) Total built up area- 988 sqm | 2.79 | 0.66 | Core structure completed, finishing work in progress | 1
5 | Const. of multi-storied building, Puri (G+2) Total built up area- 2552 sqm | 7.2 |  | Site selection finalised. Work will be started after handing over of vetted drawings to contractor. | 2 | 2.79 | 2.41
PROPOSED OFFICE BUILDINGS AS PER BUSINESS PLAN 19-24
6 | Construction of DGM office building at Khurdha (G+2) Total built-up area- 1129 sqm | 2.5 |  |  |  | 2 | 0.5
7 | Construction of office building at EHT stores sub-division, Banarpal(G+1) Total built-up area- 660 sqm | 1.5 |  |  |  | 0.5 | 1
8 | Construction of Zonal Office Building for Construction of Zone -II of OPTCL at Sambalpur (G+3) Total built-up area- 2100 sqm | 5 |  |  |  | 1.5 | 2 | 1.5
9 | Const. of EHT (O&M) division office & EMR Sub-Division Office building in 220KV Grid S/s Campus at Budhipadar, Jharsuguda.(G+3) Total built-up area- 1700 sqm | 4 |  |  |  | 2 | 2
10 | Construction of TL store cum office building inside 220/132 KV Grid S/S Tarkera(G+1) Total built-up area- 800 sqm | 2 |  |  |  | 1 | 1
[5 empty] | 8.64 | 13.87 | 11.6