## 2019-20-21
PROJECTS COMPLETED DURING FY 2019-20
Sl. No. | Name of the Project with scope of work | Scheduled date of completion | Revised date of completion | Actual Date of Charging | Original Estimated cost (Rs. Cr.) | Work order No. & Date | Revised Cost (Rs. Cr.) | Actual expenditure (unaudited) till date (Rs. Cr.) | Expected Expenditure. (Retention,BG,final reconciliation & for other pending works etc.) in Cr.
1 | 2x40MVA, 132/33kV GIS at Unit-VIII, Bhubaneswar with line | 11/2017 | 05/2019 | 01.04.2019 | 40.73 | M/s. Alstom T&D India Ltd. WO Nos.10267 & 10268 dt. 04.11.15 | 29.04 | 34.31 | 1.7
2 | 2x20MVA,132/33kV S/S at Betanoti with line | 12/2016 | 10/2018 | 19.04.2019 | 24.83 | M/s Fedders Lloyd JV M/s Jagabandhu Enterprises Pvt. Ltd. LOA Nos. 8760 & 8745 dt. 31.12.14 | 23.19 | 15.11 | 6.7
3 | 2x100MVA +2x40MVA, 220/132 / 33kV S/S at Aska with line | 06/2017 | 11/2019 | 02.06.2019 | 88.39 | M/s. Flowmore Ltd. WO Nos. 981 & 986 dt.10.02.15 | 71.18 | 80.88 | 3
4 | 2x20MVA, 220/33kV Grid S/S at Kasipur in Rayagada dist with line | 08/2016 | 03/2019 | 30.06.2019 | 28.97 | M/s Sterling & Willson, Kolkatta WO Nos. -5040 & 5045 dt. 22.08.14 | 27.96 | 30.4 | 2
5 | 132kV Bhadrak-Anandapur SC line with bay extn. at both ends | 11/2016 | 07/2019 | 03.07.2019 | 21.37 | M/s Gupta Power Infrastructure Ltd. JV M/s S.B. Electrostructural WO Nos. 2769 & 2774 dt. 31.05.14 | 23.94 | 18.51 | 4.11
6 | 2X100MVA & 2X20MVA , 220/132/33kV s/s at Jaipatana with line | 02/2018 | 12/2019 | 12.07.2019 | 88.39 | M/s Flowmore Ltd., Ranchi JV M/s Cobra WO Nos. 1012 & 1007 dt: 11.02.15 | 82.15 | 87.78 | 12.51
7 | 2x315MVA, 400kV S/S at Lapanga | 11/2016 | 08/2019 | 21.08.2019 | 126.84 | M/S GE T&D India Limited, Kolkata WO Nos. 4037 & 4042 dt. 30.05.15 | 126.84 | 142.92 | 0.199
8 | 2x20MVA, 132/33kV S/S at Agarpada with line | 08/2016 | 11/2019 | 30.08.2019 | 27.85 | M/s Jagabandhu Enterprises Pvt. Ltd. WO 4784 & 4792,dt.16.08.14 | 22.87 | 17.1 | 2.95
9 | 2x20MVA, 132/33kV S/S at Potangi | 02/2016 | 10/2018 | Line: 16.01.19 S/S: 15.09.19 | 39.23 | M/s. Sidharth Engg. Ltd. JV M/s. Sagar Steel Pvt. Ltd. LOI No. 5131 & 5136 dt.26.06.13 | 41.3 | 37.22 | 1.5
10 | 132kV Kesinga-Junagarh SC line with bay extn. at both ends. | 05/2018 | 05/2019 | 03.12.2019 | 19.65 | M/s Bajaj Electricals Ltd. WO 4144 & 4139 dt.03.06.15 | 25.27 | 23.31 | 0.2
11 | 132 kV Baner-Jaypatna (Mangalpur Megalift Proj.-12.317kms nearer to Jaypatna) D/C Line with bay extn. At Baner | 02/2020 | … | 10.01.2020 | 11.45 | M/s. Siddhartha Engineering Ltd.WO-PKG05/2018-19-29/2018/4567 dt.29.08.18 | 9.14 | 8.49 | 0.67
12 | 220kV Jayanagar(OPTCL) - Jayanagar(PGCIL) DC line | 01/2015 | 30.06.2017 | 17.01.2020 | 22.32 | M/s A.K. Das Associates, WO 4515& 4520 dt.27.07.12 | 14.61 | 16.46 | 1
13 | 132 kV Mancheswar-B to Chandaka-B, UG Cabling with bay extn. at both ends(Also 132kV UG Cabling _Mancheswar A to Mancheswar B). | 12/2019 | … | Mancheswar B to Chandaka B-26.02.2020 / Mancheswar A to Mancheswar B-charged from Mancheswar B end-16.12.2020 | 54.17 | M/s L& T,W.O.:OPTCL/PMU/132KV UG Cable/265-supply/266-Erection | 54.17 | 50.75 | 5
14 | 2x40MVA, 132/33kV GIS S/S at Mancheswar-B with line | 12/2017 | 02/2020 | 28.02.2020 | 41.53 | M/s. Alstom T&D India Ltd. W.O. 11327 & 11328 dt. 30.12.15 | 32.25 | 41.99 | 0.9
PROJECTS COMPLETED DURING FY 2020-21
Sl. No. | Name of the Project with scope of work | Scheduled date of completion | Revised date of completion | Actual Date of completion | Original Estimated cost (Rs. Cr.) | Work order No. & Date | Revised Cost (Rs. Cr.) | Actual expenditure (unaudited) till date (Rs. Cr.) | Expected Expr.(Retention,BG,final reconciliation & other pending works etc.) in Cr.
1 | 2x160MVA+2X40MVA, 220/132/33kV S/S at Godachhak and 220kV & 132kV LILO of 220kV Mermundali-Duburi & 132kV TTPS - Duburi lines. | 03/2017 | 06/2019 | 29.05.2020 | 56.34 | M/s Ashtavinayaka Construction W.O. 9510 & 9511 dt.19.09.2015 | 41.12 | 55.39 | 5
2 | 2x20MVA, 132/33kV S/S at Satasankha and 132kV DC line from proposed 220/132kV S/S at Samangara (Puri), | 06/2017 | 03/2020 | 25.06.2020 | 38.94 | M/s Flowmore Ltd. JV M/s Cobra _ W.O. 8217 & 8222 dt.03.12.2014. | 35.43 | 40.73 | 3.74
3 | One more transformer bay with one 20MVA, 220/33kV power transformer at 220/33kV Laxmipur S/S | 12/2014 | 01/2017 | 27.07.2020 | 5.93 | M/s.Empowertrans (P) Ltd. LOA 9203 & 9204 dt. 09.12.2013 | 4.44 | 5.39 | 1.2
4 | 2X20MVA, 132/33kV S/S at Brajabiharipur (CDA) Cuttack and 132kV LILO from 132kV Bidanasi-Chandaka line | 06/2017 | 03/2020 | 31.10.2020 | 37.25 | M/s A.K. Das & Associates.WO 4181 & 4176 dtd.04.06.2015 | 33.12 | 32.17 | 6.3
5 | 2x20MVA, 220/33KV AIS Grid Sub-Station at Govindpali in Malkangiri and associated LILO line.(JICA) | 01/2020 | 07/2020 | S/s charged on 17.11.2020 | 74.4 | M/s Stelmec Limited JV M/s Empower Trns Pvt. Ltd. Pkg.-JICA(5A)-03/2017-18 dt.09.01.2018 Rs. 74.40 Cr. | 76.97 | 63.19 | 8.7